## Tasks
My tasks until deployment — this week (20–24 Oct 2026)
Open tasks
Deadlines are proposed (blue = edit freely). Update Status as you go; Days left and Open tasks update by themselves.
# | Day | Task | Deadline | Depends on | Status | Days left
1 | Mon 20 Oct | Push Combined-Folder to GitHub (Ismail's 19 Oct merge + Discovery bridge) | 2026-10-20 | — | Not started
2 | Mon 20 Oct | Commit the Browse → People tab | 2026-10-20 | — | Not started
3 | Mon 20 Oct | Present the Build the Map → Discovery bridge | 2026-10-20 | — | Not started
4 | Tue 21 Oct | Send Ismail his list: migration 520/510, rollback bug, 'skip these organizations' field, organization-type filter, the 3 changes in discovery.js | 2026-10-21 | — | Not started
5 | Tue 21 Oct | Choose the contact email for Discovery and add GHUS_AGENT_CONTACT_EMAIL to .env | 2026-10-21 | Team address | Not started
6 | Tue 21 Oct | Cancel or keep the test Discovery request 'Mining organizations in the Southeast' | 2026-10-21 | — | Not started
7 | Tue 21 Oct | Review the written 13 Oct minutes | 2026-10-21 | — | Not started
8 | Tue 21 Oct | Correct the 3 claims from 13 Oct (Verify ≠ DB push; OCP/UM6P for organizations not built; questions beyond organizations not built) | 2026-10-21 | — | Not started
9 | Wed 22 Oct | Install pytest and run Ismail's 4 test files in the combined folder | 2026-10-22 | — | Not started
10 | Wed 22 Oct | Map questions, step 1: answer only from the map's card details, with sources | 2026-10-22 | — | Not started
11 | Wed 22 Oct | Remove diagnostic-only UI, keep the cost display | 2026-10-22 | Decide which parts go | Not started
12 | Wed 22 Oct | Check live that the Ask → Build the Map hand-off doesn't repeat the filters | 2026-10-22 | — | Not started
13 | Wed 22 Oct | Merge Combined-Folder into main, agreed with Ismail | 2026-10-22 | Ismail | Not started
14 | Thu 23 Oct | Run Discovery end to end once 520 is applied (Run now → Parked / Review) | 2026-10-23 | Ismail: migration 520 | Not started
15 | Thu 23 Oct | Decide where Park lives for Browse (DB status column or local store) and build the filter | 2026-10-23 | Ismail: DB column | Not started
16 | Thu 23 Oct | Test session with Fatima's scenarios; fix what it finds | 2026-10-23 | Fatima | Not started
17 | Fri 24 Oct | Deployment readiness: settings, handoff document, final full test run | 2026-10-24 | — | Not started
18 | Fri 24 Oct | Deploy the platform | 2026-10-24 | Everything above | Not started
Formulas:
Days left = IF([Status]="Done","",[Deadline]-TODAY())