## Development Plan
Platform Development Plan
Phase | Scope | Responsible | Deadline | Status | 2026-09-07 16:00 | 2026-09-14 16:00 | 2026-09-21 16:00 | 2026-09-28 16:00 | 2026-10-05 16:00
Database Architecture | Finalize the Hub, Actor, and Person table structures and relationships. | Ismail | 2026-09-11 16:00 | In progress | ◆
Build the Map Development | Connect people to organizations, add hub mapping and geography override, preserve background runs, and add completion notifications. | Nouhaila | 2026-09-15 16:00 | In progress |  | ◆
Verification Workflow | Enable Verify and Verify All and define the information shown before approval. | Nouhaila | 2026-09-11 16:00 | In progress | ◆
Data Maintenance Agent | Find and update actors and people in covered topics and apply agreed inclusion criteria. | Ismail | 2026-09-15 16:00 | In progress |  | ◆
Data Quality | Improve deduplication, record merging, re-verification, and multi-organization affiliations. | Ismail | 2026-09-16 16:00 | In progress |  | ◆
Exports | Align Excel and PowerPoint outputs with the finalized database architecture. | Nouhaila | 2026-09-11 16:00 | In progress | ◆
UI/UX Design | Define the visual identity, refine the main user journeys, and design results and verification views. | Nouhaila | 2026-09-30 16:00 | Not started |  |  |  | ◆
Testing and Management Review | Test functionality, accuracy, performance, and cost, then collect management feedback. | Nouhaila & Ismail | 2026-10-07 16:00 | Not started |  |  |  |  | ◆
Presentation and Rehearsal | Prepare the platform comparison and complete the full presentation rehearsal. | Nouhaila & Ismail | 2026-10-07 16:00 | Not started |  |  |  |  | ◆
◆